## Sheet1
Task | Submissions Made | Start Date | End Date | Day Duration
Submission | OR1/PR1 submitted | 2017-02-01 | 2017-02-02 | 2
Buffer | n/a | 2017-01-25 | 2017-02-01 | 7
Write OR and PR | TBE 1 due to LC's | 2017-01-17 | 2017-01-25 | 7
Research | n/a | 2017-01-12 | 2017-01-17 | 6
Constraints on End Solution/Project | n/a | 2017-01-16 | 2017-01-17 | 2
Pre-existing Solution | n/a | 2017-01-14 | 2017-01-15 | 2
Identify Customers/Markets | D1-Labor Costs in Lab | 2017-01-12 | 2017-01-13 | 2
Infrastructure Buillding | ability to divvy work and communicate | 2017-01-11 | 2017-01-11 | 1
Build Phase one plan | phase 1 gantt | 2017-01-10 | 2017-01-10 | 1